## Project Profile
Defect Tracking Sheet
TMT/TD05/TMP
Project ID | MMS_002
Project Name | Magento Mobile Shop
Prepared/Modified by | Role | Date of Preparation
Reviewed by | Role | Date of Review
Rutuja Kulkarni | Senior Consultant
Approved by | Role | Date of Approval
Circulation List
Version Number | <version no>

## Defect Tracking Sheet
Project ID: |  | Project Name : | [22 empty] | VERIFIED
CLOSED
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Defect Count | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments | REOPENED | Coding | Internal Dev
DF_001 | Request a Quote | Application is found unable to allow the user to contact via Skype to Admin. | Detailed Description: Application should allow the user to contact via Skype to Admin but it is unable to allow the user to contact via Skype with Admin. Steps to reproduce the bug: 1. Open the browser and website. 2. Click on "Request a Quote". 3. Click on "Let's Talk" hyperlink. Actual result observed on running the above steps: On running the above steps it is observed that application is unable to allow the user to contact via Skype with Admin which is not as expected. | Coding | Google Chrome | Internal Dev |  |  |  |  | 21-11-2018 | Alok Nanda | Rutuja Kulkarni | ACT |  | TC_UC_002
DF_002 | Blog | Application is found unable to validate the functionality of submit request tab. | Detailed Description: Application should be able to submit the request but it is found unable to validate the functionality of submit request tab. Steps TO reproduce the bug: 1. Open the browser and website 2. Click on the "Blog" tab. 3. Click on "Read more" tab. 4. Click on "Submit request". Actual result observed on running the above steps: On running the above steps it is observed that application is found unable to validate the functionality of submit request tab which is not as expected. | Coding | Google Chrome | Internal Dev |  |  |  |  | 21-11-2018 | Alok Nanda | Rutuja Kulkarni | ACT |  | TC_UC_003
DF_003 | Add-ons | Application is found unable to display the link to pay through the virtual wallet | Detailed Description: Application is found unable to display the link to pay through the virtual wallet instead displaying no option to pay through virtual wallet. Steps to reproduce the bug: 1. Open the browser and website 2. Click on the "Add-ons" tab. 3. Click on any "Add-ons". 4. Select the required items and click on Add-to Cart button to add. 5.Click on "Add" hyperlink to add wallet partial payment. 6. Click on "Proceed to Checkout" tab. 7. Enter all the mandatory details and click on "Proceed to Paypal". 8. Search for payment through virtual wallet. Actual Result observed on running the above steps: On running the above steps it is observed that application is found unable to display the link to pay through the virtual wallet which is not as expected. | Coding | Google Chrome | Internal Dev |  |  |  |  | 21-11-2018 | Alok Nanda | Rutuja Kulkarni | ACT |  | TC_UC_004
DF_004 | SignUp | Application is found unable to redirect the user to login using valid credentials. | Detailed Description: Application is found unable to redirect user to login using his valid credentials instead of redirecting the user to his/her "MY APP" page. Steps to reproduce the bug: 1. Open the Browser and website. 2. Click on Pricing tab. 3. Click on Try for free for 14 days. 4. Enter valid Email and password in the "SignUp" page. 5. Click on the "Register" button. Actual Result observed on running the above steps: On running the above steps it is observed that application is unable to redirect user to login using his valid credentials which is not as expected. | Coding | Google Chrome | Internal Dev |  |  |  |  | 21-11-2018 | Ayush Srivastava | Rutuja Kulkarni | ACT |  | TC_ST_003
DF_005 | Add-ons | Application is unable to validate the functionality of "Add to cart" without login. | Detailed Description: Application is found unable to validate the functionality of "Add to cart" without login instead of adds the product to the "Add-to-cart" without redirecting to login page. Steps to reproduce the bug: 1. Open the browser and website . 2. Click on "Add-ons" tab. 3. Click on "Add To Cart" tab. Actual Result observed on running the above steps: On running the above steps it is observed that application is found unable to validate the functionality of "Add to cart" without Login which is not as expected. | Coding | Google Chrome | Internal Dev |  |  |  |  | 21-11-2018 | Alok Nanda | Rutuja Kulkarni | ACT |  | TC_ST_004
DF_006 | Need a magento website | Application is found unable to redirecting the user to "Let’s get started" page to first register the user. | Detailed Description: Application should redirect the user to "Let’s get started" page to first register the user but it is found unable to do the same. Steps to reproduce the bug: 1. Open the browser and website 2. Click on "Need a magento website". 3. Click on "Let’s get started for free" tab. Actual result observed on running the above steps: Application is found unable to redirect user to Let's get Started page to register the user which is not as expected. | Coding | Google Chrome | Internal Dev |  |  |  |  | 21-11-2018 | Alok Nanda | Rutuja Kulkarni | ACT |  | TC_ST_005
DF_007 | Enter Your Full Name | Application is found unable to reject the invalid name in the field. | Detailed Description: Application should not accept the invalid data in the name field but it is found accepting the same. Steps To reproduce the Bug: 1. Open the browser and the website. 2. Click on Let's Get Started tab. 3. Enter invalid data in the Enter your full name field. Actual Result observed on running the above steps: On running the above steps it is observed that Application is accepting the invalid data in the name field which is not as expected. | Coding | Google Chrome | Internal Dev |  |  |  |  | 21-11-2018 | Alok Nanda | Rutuja Kulkarni | ACT |  | TC_CE_002
DF_008 | Get Started | Application is found unable to redirect the user to login page. | Detailed Description: Application should redirect the user to login page but it is found redirecting the user to his/her My App page. Steps to Reproduce the bug: 1. Open the browser and the website 2. Click on Let's Get Started!! Tab 3. Enter Your Full Name 4.Enter Email id. 5. Enter Password . 6. Click on Get Started Button. Actual result observed on running the above steps: On running the above steps it is observed that Application is redirecting the user to his/her My App page which is not as expected. | Coding | Google Chrome | Internal Dev |  |  |  |  | 21-11-2018 | Alok Nanda | Rutuja Kulkarni | ACT |  | TC_CE_006
DF_009 | Behaviour of Application on Network failure | Application is found unable to redirect the user to login page to login to the application. | Detailed Description: Application should redirect user to login page and ask the user to login after a network failure but it is found unable to do the same and it allows users to perform operations. Steps To Reproduce the bug: 1. Open the browser and the website 2. Click on the "Login Tab" . 3. Enter Valid credentials. 4. Click on Login Button. 5. Switch the network off 6. Switch the network on 7. Explore the Application Actual Result Observed on running the above steps: On running the above steps it is observed that Application is allowing the user to perform other operations without login to the application which is not as expected. | Coding | Google Chrome | Internal Dev |  |  |  |  | 21-11-2018 | Alok Nanda | Rutuja Kulkarni | ACT |  | TC_S_001
DF_010 | Behaviour of Application on Power failure | Application is found unable to redirect the user to login page to login to the application after a power failure. | Detailed Description: Application should redirect user to login page and ask the user to login if there is a power failure but it is found unable to do the same and it allows users to perform operations. Steps To Reproduce the bug: 1. Open the browser and the website 2. Click on the "Login Tab" . 3. Enter Valid credentials. 4. Click on Login Button. 5. Switch the network off 6. Switch the network on 7. Explore the Application Actual Result Observed on running the above steps: On running the above steps it is observed that Application is allowing the user to perform other operations without login to the application after recovery from a power failure which is not as expected. | Coding | Google Chrome | Internal Dev |  |  |  |  | 21-11-2018 | Alok Nanda | Rutuja Kulkarni | ACT |  | TC_S_002
DF_011 | Forcefully Application Closure | Application is found unable to display an alert box asking for closure of the Application before closure of it. | Detailed Description: Application should display an alert box asking for closure of the Application but it is found that application gets closed directly. Steps TO reproduce the bug: 1. Open the browser and the website 2. Click on close of the browser. Actual Result observed on running the above steps: On running the above steps it is observed that Application is closing the application without any alert which is not as expected. | Coding | Google Chrome | Internal Dev |  |  |  |  | 21-11-2018 | Alok Nanda | Rutuja Kulkarni | ACT |  | TC_S_006
DF_012 | Idle waiting time | Application is found unable to redirect the user to the Login Page. | Detailed Description: Application should redirect the user to the Login Page but it is found allowing the user to work efficiently. Steps To Reproduce the Bug: 1. Open the browser and the website 2. Leave the website idle for 10 minutes Actual Result observed on running the above steps: On running the above steps it is observed that Application is allowing the user to work efficiently which is not as expected. | Coding | Google Chrome | Internal Dev |  |  |  |  | 21-11-2018 | Alok Nanda | Rutuja Kulkarni | ACT |  | TC_S_007
DF_013 | Autofill Username | Application is found unable to not show already entered username in username textfield | Detailed Description: Application should not show already entered username in username textfield but it is found displaying the already entered username in the textfield. Steps To reproduce the bug: 1. Open the browser and the website 2. Click on the "Login Tab" . 3. Enter the username . 4. enter the password 5. Click on Login Button. 6. User should close the Application forcecfully 7. User Should again Open the login page. 8. User should check the visibilty of username Actual Result observed on running the above steps: On running the above steps it is observed that Application is displaying the already entered username in the textfield which is not as expected. | Coding | Google Chrome | Internal Dev |  |  |  |  | 21-11-2018 | Alok Nanda | Rutuja Kulkarni | ACT |  | TC_S_008
DF_013 | Add-ons | Application is found unable to display a link to pay through virtual wallet. | Detailed Description: Application should display a link to pay through virtual wallet but it is found there is no option displaying to pay through virtual wallet. Steps to reproduce the bug: 1. Open the browser and the website 2. Click on the "Add-ons" tab. 3. Click on any "Add-ons". 4. Select the required items and click on Add-to Cart button to add. 5.Click on "Add" hyperlink to add wallet partial payment. 6. Click on "Proceed to Checkout" tab. 7. Enter all the mandatory details and click on "Proceed to Paypal". 8. Search for payment through virtual wallet. Actual Result observed on running the above steps: On running the above steps it is observed that there is no option displaying to pay through virtual wallet which is not as expected. | Coding | Google Chrome | Internal Dev |  |  |  |  | 21-11-2018 | Alok Nanda | Rutuja Kulkarni | ACT |  | TC_IS_006
DF_013 | Pricing | Application is found unable to redirect the user to "MYAPP" page. | Detailed Description: Application should redirect the user to "MyApp" page but it is found throwing an error message "The password field is empty." Steps To Reproduce the bug: 1. Open the browser and the website 2. Click on the "Pricing" tab. 3. Click on "Try for free for 14 days. 4.User should Register/Login with valid credentials. 5. Click on the "Get Started" tab in "Platinum" plan. 6.User should Register/Login with valid credentials. 7. Click on the "Get Started" tab in "Platinum" plan. 8.User should Register/Login with valid credentials. Actual Result observed on running the above steps: On running the above steps it is observed that Application is throwing an error message "The Password field is empty" which is not as expected. | Coding | Google Chrome | Internal Dev |  |  |  |  | 21-11-2018 | Alok Nanda | Rutuja Kulkarni | ACT |  | TC_IS_007
Note on A3: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B3: Alphy Chenganiyadan: Give the name of the module being tested
Note on C3: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D3: Alphy Chenganiyadan: A detailed description of the defect
Note on E3: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F3: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G3: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I3: Prioritize the defect
Note on J3: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K3: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L3: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M3: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N3: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O3: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P3: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q3: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on S3: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T3: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U3: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V3: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W3: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X3: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y3: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.

## Revision History
REVISION HISTORY OF WORK PRODUCT (to be maintained by projects)
# | Date | Version # | Section Changed | Details of changes made | Approved By